## 6-12 months
Health Fair Checklist and Timeline
To be completed by:
Deadline:
Six to twelve months before the health fair | Due By | Notes
Secure agreement from senior management/host organization.
Identify target audience(s).
Establish goals, objectives, and timelines for the health fair.
Select planning committee members; appoint chair/co-chairs.
Form and meet with subcommittees.
Select subcommittee chairs to report activities to the planning committee.
Identify partner organizations that might co-host the fair (if relevant).
Provide stipend to host organization (if relevant).
Select a theme.
Select dates and times.
Select and reserve the fair location/venue.
Make sure there are enough electrical cords and outlets for testing and audiovisual equipment at location.
Preliminarily identify tests, services, information, exhibits, activities.
Prepare a budget:
· Calculate & monitor food budget
· Calculate & monitor educational materials budget
· Calculate & monitor supplies/kits budget
Other:
Other:
Other:
Other:

## Unconfirmed Vendors (hidden)
Vendor | Person Contacting
NJQuitline | Nancy S.
American Diabetes Association | Nancy S.
American Heart Association | Nancy S.
Planned Parenthood | Nancy S.
Wellness Institute at the Hilton | Dai
NAMI | Mark W.
Massage Therapist | Nancy
Pet therapy | Nancy
Wells Fargo | Kathy
CEC—Economic Development Services | John G.
Service Participant Jewelry business | Nancy

## Vendor Listing (hidden)
Vendor Listing
| Vendors | Confirmed | Person Contacting | Room Placement | Notes |  | Yes
1 | Clark Shoprite | Yes | Kathy |  | Have a table--will provide food |  | No
2 | Jansen | No | Kathy |  | Medication Education
3 | Neighborhood Health Center | Yes | Nancy S.
4 | Rutgers Coop Snap-Ed | Yes | Nancy S. |  | Nutritional Program for people with Food Stamps
6 | American Diabetes Association | No | Nancy S.
7 | American Heart Association | No | Nancy S.
8 | Planned Parenthood- Elizabeth | No | Kathy P.
9 | Horizon BCBS | Yes | Shanae |  | Confirmed 2 hours--9am-1 | Share Table
10 | Bally’s Total Fitness | Yes | Shanae |  | 1-3pm confirmed
11 | Wellness Institute at the Hilton | No | Dai |  | If not confirmed, there is an alternative option
12 | Newark Behavioral Health Center | Yes | Debra
13 | New Concept Cosmetology School | Yes | Debra/Miriam
14 | NAMI-NJ | Yes | Mark W. |  | Offering table
15 | Massage Therapist | No | Nancy P.
16 | Pet therapy | No | Nancy P.
Vendor Listing
17 | Bridgeway Career Services | Yes | John
18 | Wells Fargo | Yes | Kathy S.
19 | CEC—Economic Development Services | Yes | John G.
20 | PSR Dept./Wellness for Life | Yes | Michelle Z.
21 | UMDNJ- Physical Therapy Dept. | No | Michelle Z. |  | Interested but checking with chariperson
22 | UMDNJ- Dental Dept. | No | Ann M.
23 | UMDNJ-Dietetics Dept. | No | Lia L.
24 | UMDNJ- Cytotechnology Dept. | Yes | Lia L. |  | Provide education on lab testing in general, lab tests used in health screening, and tests for cancer screening
25 | UMDNJ- Physicians Assistants Dept. | No | Ann M. and Michelle Z. |  | The Physician's Assistants Dept. may be able to assist with the actual screening process.
26 | Barnabas Health Institute for Prevention | Yes | Nancy |  | Offering Smoking Cessation Screening

## 4-6 months
Health Fair Checklist and Timeline
Four to six months before the health fair | Due By | Notes
Identify & secure commitments from nurses/medical personnel administering health tests/screeings.
Verify current licensure of nurses/medical personnel.
Select health screenings and services to be offered.
Develop and obtain approval for Emergency Protocol.
Identify and secure commitments from vendors and exhibitors.
Identify and secure commitments from donors.
Secure volunteers, including someone who can take pictures the day of the fair.
Ask all staff, volunteers, and exhibitors to reserve the selected date.
Begin planning to accommodate for any child care or other special needs of attendees.
Reserve rental equipment, including privacy screens if using.
Determine refrigeration needs prior to & during the fair.
Reserve tables and chairs.
Design and order staff/volunteer t-shirts based on theme.
Other:
Other:
Other:
Other:

## 3 months
Health Fair Checklist and Timeline
Three months before the health fair | Due By | Notes
Meet with subcommittee chairs to review progress towards implementation of plans.
Order Medical Fact Sheets and education materials from professional organizations.
Develop and proofread materials to publicize the event (posters, flyers, PSAs)
Duplicate printed materials, such as registration forms, Results Recording Forms, Health Passports, and Satisfaction Surveys.
Plan for and begin securing freebies, giveaways, decorations.
Create and send written confirmation to exhibitors and donors.
Monitor exhibitor and donor responses; follow up with non-responders.
Secure cash box; plan for change needs at the fair.
Reserve handtrucks and carts.
Reserve trash receptacles and containers for biohazardous materials.
Review Planning/Supplies Spreadsheet and order the supplies (test kits, wristbands, the scale, tape measure, tablecloths, etc.)
Make arrangements to safely store test kits that need to be refrigerated.
Make arrangements to secure a laptop and TV/DVD player, if needed.
Begin planning for attendees' transportation needs.
Create lists with contact information of volunteers and exhibitors.
Secure items for Break Room and Respite Room (if using).
Other:
Other:
Other:
Other:

## 1 month
Health Fair Checklist and Timeline
One month before the health fair | Due By | Notes
Meet with subcommittee chairs to review progress towards implementation of plans.
Publicize the event with flyers, posters, etc.
Contact television, radio, and newspapers to publicize, if relevant.
Plan lay-out for stations, booths, and exhibits.
Make station and booth signs.
Create map for exhibitors and attendees.
Make the program, acknowledging exhibitors, volunteers, donors, etc.
Make a list of items that still need to be purchased (see Planning/Supplies Spreadsheet)
Secure supplies for the “be prepared for anything kit” (see Planning/Supplies Spreadsheet)
If using pre-registration, begin registering attendees to determine schedule, staffing, needed outreach
Train fair volunteers and staff; arrange for practice sessions
Develop and print signs for stations.
Obtain certificate/waiver of insurance for fair venue, if needed.
Other:
Other:
Other:
Other:

## 1 week
Health Fair Checklist and Timeline
One week before the health fair | Due By | Notes
Issue reminders to attendees and host organization staff.
Create and finalize staff and volunteer schedules.
Confirm with all attendees.
Confirm with all volunteers and staff.
Finalize plan for staffing, including command center table.
Finalize map for exhibitors, volunteers, staff, and attendees; print.
Finalize and print health fair program.
Ensure educational materials for each station are finalized and printed.
Confirm with all exhibitors (acquire exhibitor resources as needed).
Determine total number in attendance expected.
Make nametags for staff/volunteers.
Purchase and safely store non-perishable snacks and beverages for volunteers and attendees.
Develop schedule to assign staff/volunteers to each station/booth.
Finalize plan for the registration table and registration process.
Finalize plan for event evaluation, including distribution and collection.
Prepare the goody bags, if using.
Other:
Other:
Other:
Other:

## 1 day
Health Fair Checklist and Timeline
Day before the health fair | Due By | Notes
Set up tables, booths, exhibits, waiting area, etc.
Bring the “be prepared for anything kit.”
Label the command center table and equip it with the “be prepared for anything kit.”
Set up the registration table (include registration sheets, pens, maps, etc.)
Set up the evaluation area, including satisfaction surveys for exhibitors and participants.
Purchase and safely store perishable food (lunch, apples for snacks, etc.) for staff, volunteers, and attendees.
Set up the food area.
Set up the Break Room and Respite Room.
Other:
Other:
Other:
Other:

## Day of Fair
Health Fair Checklist and Timeline
Day of the health fair | Due By | Notes
Finish setting up.
Be ready one hour before opening.
Direct and instruct volunteers.
Greet vendors and escort them to their exhibit spaces.
Collect registrations, station results recording forms, etc.
Collect satisfaction evaluations.
Clean up.
Record final number of attendees.
Other:
Other:
Other:
Other:
Day of the fair checklist | Due By | Notes
Did you set up early?
Are there signs to direct people where to go?
Are the food & beverages for staff, volunteers, exhibitors, and attendees set?
Has the audiovisual equipment been tested on-site by those individuals who will be using it?
Is there enough seating?
Does the set-up promote an adequate flow of participants to each event?
Are there enough educational materials and handouts for participants?
Do you have pens available for participants to complete satisfaction surveys, forms, etc.?
Do you have the gift bags, freebies, give-aways, etc.?
Other:
Other:
Other:
Other:

## Post-Fair
Health Fair Checklist and Timeline
Follow-up after the fair | Due By | Notes
Send thank you letters to exhibitors, volunteers, etc.
If feasible, check with agencies providing attendees to ensure follow-up is done for test results.
Tabulate satisfaction survey results.
Determine and document possible improvements for next time.
Report results to the senior management, exhibitors, media, etc., as appropriate.
Submit all receipts to appropriate parties
Other:
Other:
Other:
Other: